## Kids Sunstick
Kids Sunstick — GTM Schedule
Launch: DTC May 19 / Sephora Jun 30 ¦ Start: 2025-02-11 ¦ Total: 69 business days ¦ Tasks: 35
📌 MULTI-DEPENDENCY RULE: When a task has multiple dependencies, it starts after ALL are complete — the scheduler uses the LATEST dependency due date as the starting point.
# | Task Name | Phase | Owner | Lead Time | Start Date | Due Date | Dependencies | Multi-Dep Logic | Flags / Notes
▸ CONTENT PLANNING
1 | Product Sheet & Competitive Landscape | Content Planning | Marketing | 3 BD | 2025-02-11 | 2025-02-14 | — ROOT (no dependencies) | Backward-computed from launch date | First task — start date computed backward from launch date
2 | Draft Product Positioning & Messaging | Content Planning | Marketing | 3 BD | 2025-02-14 | 2025-02-19 | Product Sheet & Competitive Landscape (due 2025-02-14) | Single dep: Product Sheet & Competitive Landscape Due 2025-02-14 → Start → +3BD = 2025-02-19
3 | 📅 GTM Brainstorm Meeting | Content Planning | Marketing | 3 BD | 2025-02-19 | 2025-02-24 | Draft Product Positioning & Messaging (due 2025-02-19) | Single dep: Draft Product Positioning & Messaging Due 2025-02-19 → Start → +3BD = 2025-02-24 | 📅 Meeting (lead time = scheduling window) Align on: positioning, marketing pillars, creative concepts, bundle assortment, retail channel presence
4 | Finalize Product Positioning & Messaging | Content Planning | Marketing | 3 BD | 2025-02-24 | 2025-02-27 | GTM Brainstorm Meeting (due 2025-02-24) | Single dep: GTM Brainstorm Meeting Due 2025-02-24 → Start → +3BD = 2025-02-27
5 | Finalize Creative Shoot Plan | Content Planning | Creative | 3 BD | 2025-02-24 | 2025-02-27 | GTM Brainstorm Meeting (due 2025-02-24) | Single dep: GTM Brainstorm Meeting Due 2025-02-24 → Start → +3BD = 2025-02-27
6 | Finalize Bundle Assortment | Content Planning | Growth | 3 BD | 2025-02-24 | 2025-02-27 | GTM Brainstorm Meeting (due 2025-02-24) | Single dep: GTM Brainstorm Meeting Due 2025-02-24 → Start → +3BD = 2025-02-27
7 | Finalize 360 GTM Plan & Retail Channels | Content Planning | Leadership | 3 BD | 2025-02-24 | 2025-02-27 | GTM Brainstorm Meeting (due 2025-02-24) | Single dep: GTM Brainstorm Meeting Due 2025-02-24 → Start → +3BD = 2025-02-27
8 | Finalize Email Plan | Content Planning | Growth | 3 BD | 2025-02-24 | 2025-02-27 | GTM Brainstorm Meeting (due 2025-02-24) | Single dep: GTM Brainstorm Meeting Due 2025-02-24 → Start → +3BD = 2025-02-27
9 | Submit Tagline + Campaign Copy Brief | Content Planning | Marketing | 3 BD | 2025-02-27 | 2025-03-04 | Finalize Product Positioning & Messaging (due 2025-02-27) | Single dep: Finalize Product Positioning & Messaging Due 2025-02-27 → Start → +3BD = 2025-03-04
▸ FINALIZE & INFORM MGMT
10 | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 3 BD | 2025-02-27 | 2025-03-04 | Finalize Product Positioning & Messaging (due 2025-02-27) Finalize Bundle Assortment (due 2025-02-27) Finalize 360 GTM Plan & Retail Channels (due 2025-02-27) | Waits for ALL 3 deps. Latest dep due: 2025-02-27 Start = 2025-02-27 → Due = +3BD = 2025-03-04 | Align on: final taglines, final 360 GTM plan, bundle assortment. Requires all brainstorm outputs.
▸ DESIGN PRODUCTION
11 | Draft Email Briefs | Design Production | Marketing | 3 BD | 2025-02-27 | 2025-03-04 | Finalize Email Plan (due 2025-02-27) | Single dep: Finalize Email Plan Due 2025-02-27 → Start → +3BD = 2025-03-04 | Email campaign briefs based on finalized email plan from Growth.
▸ CONTENT PRODUCTION
12 | Draft Asset Request Form | Content Production | Marketing | 3 BD | 2025-03-04 | 2025-03-07 | Final GTM Deck (due 2025-03-04) | Single dep: Final GTM Deck Due 2025-03-04 → Start → +3BD = 2025-03-07
13 | Samples Available | Content Production | Ops | 10 BD | 2025-02-21 | 2025-03-07 | — ROOT (no dependencies) | Backward-computed from launch date | Product samples must be physically available 2 weeks (10 BD) before shoots. Due date auto-computed from shoot dates.
▸ CONTENT PLANNING
14 | R1 Taglines & Copy Due | Content Planning | Copywriter | 5 BD | 2025-03-04 | 2025-03-11 | Submit Tagline + Campaign Copy Brief (due 2025-03-04) | Single dep: Submit Tagline + Campaign Copy Brief Due 2025-03-04 → Start → +5BD = 2025-03-11
▸ CONTENT PRODUCTION
15 | Finalize Social Strategy | Content Production | Social | 5 BD | 2025-03-04 | 2025-03-11 | Final GTM Deck (due 2025-03-04) | Single dep: Final GTM Deck Due 2025-03-04 → Start → +5BD = 2025-03-11
▸ DESIGN PRODUCTION
16 | Draft Social Creative Briefs | Design Production | Social | 3 BD | 2025-03-11 | 2025-03-14 | Finalize Social Strategy (due 2025-03-11) | Single dep: Finalize Social Strategy Due 2025-03-11 → Start → +3BD = 2025-03-14 | Social creative direction briefs based on finalized social strategy.
▸ CONTENT PLANNING
17 | Tagline / Copy Iteration | Content Planning | Copywriter | 5 BD | 2025-03-11 | 2025-03-18 | R1 Taglines & Copy Due (due 2025-03-11) | Single dep: R1 Taglines & Copy Due Due 2025-03-11 → Start → +5BD = 2025-03-18
▸ CONTENT PRODUCTION
18 | Finalize Asset Requests | Content Production | Marketing | 10 BD | 2025-03-07 | 2025-03-21 | Draft Asset Request Form (due 2025-03-07) | Single dep: Draft Asset Request Form Due 2025-03-07 → Start → +10BD = 2025-03-21 | Meet with creative during this time to align on all assets needed
▸ CONTENT PLANNING
19 | Final Taglines & Campaign Copy Due | Content Planning | Marketing | 5 BD | 2025-03-18 | 2025-03-25 | Tagline / Copy Iteration (due 2025-03-18) | Single dep: Tagline / Copy Iteration Due 2025-03-18 → Start → +5BD = 2025-03-25
▸ CONTENT PRODUCTION
20 | Lifestyle Shoot | Content Production | Creative | 5 BD | 2025-03-21 | 2025-03-28 | Finalize Asset Requests (due 2025-03-21) Finalize Creative Shoot Plan (due 2025-02-27) Samples Available (due 2025-03-07) | Waits for ALL 3 deps. Latest dep due: 2025-03-21 Start = 2025-03-21 → Due = +5BD = 2025-03-28 | Week-long scheduling window. Depends on: asset requests finalized (what to shoot), creative shoot plan (how to shoot), product samples (what to shoot with).
21 | Product Shoot | Content Production | Creative | 5 BD | 2025-03-21 | 2025-03-28 | Finalize Asset Requests (due 2025-03-21) Finalize Creative Shoot Plan (due 2025-02-27) Samples Available (due 2025-03-07) | Waits for ALL 3 deps. Latest dep due: 2025-03-21 Start = 2025-03-21 → Due = +5BD = 2025-03-28 | Week-long scheduling window. Can run in parallel with or right after Lifestyle Shoot.
▸ DESIGN PRODUCTION
22 | Draft PDP Gallery Asset Briefs | Design Production | Marketing | 3 BD | 2025-03-25 | 2025-03-28 | Final Taglines & Campaign Copy Due (due 2025-03-25) | Single dep: Final Taglines & Campaign Copy Due Due 2025-03-25 → Start → +3BD = 2025-03-28 | PDP gallery image & asset briefs based on final approved taglines/copy.
▸ CONTENT PRODUCTION
23 | Start Sourcing Creators | Content Production | Influencer | 15 BD | 2025-03-11 | 2025-04-01 | Finalize Social Strategy (due 2025-03-11) | Single dep: Finalize Social Strategy Due 2025-03-11 → Start → +15BD = 2025-04-01 | Lead time set to ensure sourcing starts early enough
▸ DESIGN PRODUCTION
24 | 📅 Brief Alignment Meeting | Design Production | Marketing | 3 BD | 2025-03-28 | 2025-04-02 | Draft Email Briefs (due 2025-03-04) Draft PDP Gallery Asset Briefs (due 2025-03-28) Draft Social Creative Briefs (due 2025-03-14) | Waits for ALL 3 deps. Latest dep due: 2025-03-28 Start = 2025-03-28 → Due = +3BD = 2025-04-02 | 📅 Meeting (lead time = scheduling window) Requires ALL 3 draft briefs to be complete before meeting can be scheduled.
▸ CONTENT PRODUCTION
25 | 📅 Creator Review Meeting | Content Production | Influencer | 3 BD | 2025-04-01 | 2025-04-04 | Start Sourcing Creators (due 2025-04-01) | Single dep: Start Sourcing Creators Due 2025-04-01 → Start → +3BD = 2025-04-04 | 📅 Meeting (lead time = scheduling window)
▸ DESIGN PRODUCTION
26 | Asset Design Briefs Due | Design Production | Marketing | 5 BD | 2025-04-02 | 2025-04-09 | Brief Alignment Meeting (due 2025-04-02) | Single dep: Brief Alignment Meeting Due 2025-04-02 → Start → +5BD = 2025-04-09 | Finalized design briefs incorporating alignment meeting feedback.
▸ CONTENT PRODUCTION
27 | Photo Selects Ready | Content Production | Creative | 10 BD | 2025-03-28 | 2025-04-11 | Lifestyle Shoot (due 2025-03-28) Product Shoot (due 2025-03-28) | Waits for ALL 2 deps. Latest dep due: 2025-03-28 Start = 2025-03-28 → Due = +10BD = 2025-04-11 | ~2 weeks for photo selects/retouching from both shoots. These feed into R1 Assets.
28 | Briefs to Creators | Content Production | Influencer | 5 BD | 2025-04-04 | 2025-04-11 | Creator Review Meeting (due 2025-04-04) Samples Available (due 2025-03-07) | Waits for ALL 2 deps. Latest dep due: 2025-04-04 Start = 2025-04-04 → Due = +5BD = 2025-04-11 | Needs BOTH: creator list confirmed (from review meeting) AND product samples ready (to send with briefs).
▸ DESIGN PRODUCTION
29 | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 10 BD | 2025-04-11 | 2025-04-25 | Asset Design Briefs Due (due 2025-04-09) Photo Selects Ready (due 2025-04-11) | Waits for ALL 2 deps. Latest dep due: 2025-04-11 Start = 2025-04-11 → Due = +10BD = 2025-04-25 | First round of all design assets. Requires BOTH: finalized briefs AND photo selects from shoots. ~2 weeks for creative to produce.
30 | Asset Feedback Due | Design Production | Marketing | 3 BD | 2025-04-25 | 2025-04-30 | R1 Assets Due (Email, Social, PDP) (due 2025-04-25) | Single dep: R1 Assets Due (Email, Social, PDP) Due 2025-04-25 → Start → +3BD = 2025-04-30
▸ CONTENT PRODUCTION
31 | Creator Content Delivered | Content Production | Influencer | 15 BD | 2025-04-11 | 2025-05-02 | Briefs to Creators (due 2025-04-11) | Single dep: Briefs to Creators Due 2025-04-11 → Start → +15BD = 2025-05-02
▸ DESIGN PRODUCTION
32 | Sephora Final Assets Due | Design Production | Creative | 5 BD | 2025-04-30 | 2025-05-07 | Asset Feedback Due (due 2025-04-30) | Single dep: Asset Feedback Due Due 2025-04-30 → Start → +5BD = 2025-05-07 | 🏪 Anchored to Sephora launch date
33 | DTC & Amazon Final Assets Due | Design Production | Creative | 5 BD | 2025-04-30 | 2025-05-07 | Asset Feedback Due (due 2025-04-30) | Single dep: Asset Feedback Due Due 2025-04-30 → Start → +5BD = 2025-05-07
34 | Draft Sephora Catalog & PDP Copy Due | Design Production | Marketing | 5 BD | 2025-05-07 | 2025-05-14 | DTC & Amazon Final Assets Due (due 2025-05-07) | Single dep: DTC & Amazon Final Assets Due Due 2025-05-07 → Start → +5BD = 2025-05-14
35 | Final DTC PDP Copy & Reviews Due | Design Production | Marketing | 3 BD | 2025-05-14 | 2025-05-19 | Draft Sephora Catalog & PDP Copy Due (due 2025-05-14) | Single dep: Draft Sephora Catalog & PDP Copy Due Due 2025-05-14 → Start → +3BD = 2025-05-19
LEGEND
Phase colors: | Green = Content Planning, Yellow = Finalize & Mgmt, Blue = Content Production, Pink = Design Production
🔒 Partner Anchor: | Hard-coded date from external partner (e.g., Mattel). Highest priority — everything schedules around it.
⚠️ Compressed: | Task has less time than its lead time requires. Red highlight = needs attention.
🏪 Channel Anchor: | Task anchored to a specific channel launch date (e.g., Sephora) instead of DTC.
📅 Meeting: | Lead time = scheduling window. Actual meeting is 1 day.
Multi-Dep Rule: | When a task depends on multiple predecessors, it starts after ALL are done (uses the LATEST due date).

## Polly Pocket
Polly Pocket — GTM Schedule
Launch: DTC Aug 4 / Mattel anchor Jul 15 ¦ Start: 2025-04-21 ¦ Total: 75 business days ¦ Tasks: 34
📌 MULTI-DEPENDENCY RULE: When a task has multiple dependencies, it starts after ALL are complete — the scheduler uses the LATEST dependency due date as the starting point.
# | Task Name | Phase | Owner | Lead Time | Start Date | Due Date | Dependencies | Multi-Dep Logic | Flags / Notes
▸ CONTENT PLANNING
1 | Product Sheet & Competitive Landscape | Content Planning | Marketing | 3 BD | 2025-04-21 | 2025-04-24 | — ROOT (no dependencies) | Backward-computed from launch date | First task — start date computed backward from launch date
2 | Draft Product Positioning & Messaging | Content Planning | Marketing | 3 BD | 2025-04-24 | 2025-04-29 | Product Sheet & Competitive Landscape (due 2025-04-24) | Single dep: Product Sheet & Competitive Landscape Due 2025-04-24 → Start → +3BD = 2025-04-29
3 | 📅 GTM Brainstorm Meeting | Content Planning | Marketing | 3 BD | 2025-04-29 | 2025-05-02 | Draft Product Positioning & Messaging (due 2025-04-29) | Single dep: Draft Product Positioning & Messaging Due 2025-04-29 → Start → +3BD = 2025-05-02 | 📅 Meeting (lead time = scheduling window) Align on: positioning, marketing pillars, creative concepts, bundle assortment, retail channel presence
4 | Finalize Product Positioning & Messaging | Content Planning | Marketing | 3 BD | 2025-05-02 | 2025-05-07 | GTM Brainstorm Meeting (due 2025-05-02) | Single dep: GTM Brainstorm Meeting Due 2025-05-02 → Start → +3BD = 2025-05-07
5 | Finalize Creative Shoot Plan | Content Planning | Creative | 3 BD | 2025-05-02 | 2025-05-07 | GTM Brainstorm Meeting (due 2025-05-02) | Single dep: GTM Brainstorm Meeting Due 2025-05-02 → Start → +3BD = 2025-05-07
6 | Finalize Bundle Assortment | Content Planning | Growth | 3 BD | 2025-05-02 | 2025-05-07 | GTM Brainstorm Meeting (due 2025-05-02) | Single dep: GTM Brainstorm Meeting Due 2025-05-02 → Start → +3BD = 2025-05-07
7 | Finalize 360 GTM Plan & Retail Channels | Content Planning | Leadership | 3 BD | 2025-05-02 | 2025-05-07 | GTM Brainstorm Meeting (due 2025-05-02) | Single dep: GTM Brainstorm Meeting Due 2025-05-02 → Start → +3BD = 2025-05-07
8 | Finalize Email Plan | Content Planning | Growth | 3 BD | 2025-05-02 | 2025-05-07 | GTM Brainstorm Meeting (due 2025-05-02) | Single dep: GTM Brainstorm Meeting Due 2025-05-02 → Start → +3BD = 2025-05-07
9 | Submit Tagline + Campaign Copy Brief | Content Planning | Marketing | 3 BD | 2025-05-07 | 2025-05-12 | Finalize Product Positioning & Messaging (due 2025-05-07) | Single dep: Finalize Product Positioning & Messaging Due 2025-05-07 → Start → +3BD = 2025-05-12
▸ FINALIZE & INFORM MGMT
10 | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 3 BD | 2025-05-07 | 2025-05-12 | Finalize Product Positioning & Messaging (due 2025-05-07) Finalize Bundle Assortment (due 2025-05-07) Finalize 360 GTM Plan & Retail Channels (due 2025-05-07) | Waits for ALL 3 deps. Latest dep due: 2025-05-07 Start = 2025-05-07 → Due = +3BD = 2025-05-12 | Align on: final taglines, final 360 GTM plan, bundle assortment. Requires all brainstorm outputs.
▸ DESIGN PRODUCTION
11 | Draft Email Briefs | Design Production | Marketing | 3 BD | 2025-05-07 | 2025-05-12 | Finalize Email Plan (due 2025-05-07) | Single dep: Finalize Email Plan Due 2025-05-07 → Start → +3BD = 2025-05-12 | Email campaign briefs based on finalized email plan from Growth.
▸ CONTENT PRODUCTION
12 | Draft Asset Request Form | Content Production | Marketing | 3 BD | 2025-05-12 | 2025-05-15 | Final GTM Deck (due 2025-05-12) | Single dep: Final GTM Deck Due 2025-05-12 → Start → +3BD = 2025-05-15
13 | Samples Available | Content Production | Ops | 10 BD | 2025-05-01 | 2025-05-15 | — ROOT (no dependencies) | Backward-computed from launch date | Product samples must be physically available 2 weeks (10 BD) before shoots. Due date auto-computed from shoot dates.
▸ CONTENT PLANNING
14 | R1 Taglines & Copy Due | Content Planning | Copywriter | 5 BD | 2025-05-12 | 2025-05-19 | Submit Tagline + Campaign Copy Brief (due 2025-05-12) | Single dep: Submit Tagline + Campaign Copy Brief Due 2025-05-12 → Start → +5BD = 2025-05-19
▸ CONTENT PRODUCTION
15 | Finalize Social Strategy | Content Production | Social | 5 BD | 2025-05-12 | 2025-05-19 | Final GTM Deck (due 2025-05-12) | Single dep: Final GTM Deck Due 2025-05-12 → Start → +5BD = 2025-05-19
▸ DESIGN PRODUCTION
16 | Draft Social Creative Briefs | Design Production | Social | 3 BD | 2025-05-19 | 2025-05-22 | Finalize Social Strategy (due 2025-05-19) | Single dep: Finalize Social Strategy Due 2025-05-19 → Start → +3BD = 2025-05-22 | Social creative direction briefs based on finalized social strategy.
▸ CONTENT PLANNING
17 | Tagline / Copy Iteration | Content Planning | Copywriter | 5 BD | 2025-05-19 | 2025-05-26 | R1 Taglines & Copy Due (due 2025-05-19) | Single dep: R1 Taglines & Copy Due Due 2025-05-19 → Start → +5BD = 2025-05-26
▸ CONTENT PRODUCTION
18 | Finalize Asset Requests | Content Production | Marketing | 10 BD | 2025-05-15 | 2025-05-29 | Draft Asset Request Form (due 2025-05-15) | Single dep: Draft Asset Request Form Due 2025-05-15 → Start → +10BD = 2025-05-29 | Meet with creative during this time to align on all assets needed
▸ CONTENT PLANNING
19 | Final Taglines & Campaign Copy Due | Content Planning | Marketing | 5 BD | 2025-05-26 | 2025-06-02 | Tagline / Copy Iteration (due 2025-05-26) | Single dep: Tagline / Copy Iteration Due 2025-05-26 → Start → +5BD = 2025-06-02
▸ CONTENT PRODUCTION
20 | Lifestyle Shoot | Content Production | Creative | 5 BD | 2025-05-29 | 2025-06-05 | Finalize Asset Requests (due 2025-05-29) Finalize Creative Shoot Plan (due 2025-05-07) Samples Available (due 2025-05-15) | Waits for ALL 3 deps. Latest dep due: 2025-05-29 Start = 2025-05-29 → Due = +5BD = 2025-06-05 | Week-long scheduling window. Depends on: asset requests finalized (what to shoot), creative shoot plan (how to shoot), product samples (what to shoot with).
21 | Product Shoot | Content Production | Creative | 5 BD | 2025-05-29 | 2025-06-05 | Finalize Asset Requests (due 2025-05-29) Finalize Creative Shoot Plan (due 2025-05-07) Samples Available (due 2025-05-15) | Waits for ALL 3 deps. Latest dep due: 2025-05-29 Start = 2025-05-29 → Due = +5BD = 2025-06-05 | Week-long scheduling window. Can run in parallel with or right after Lifestyle Shoot.
▸ DESIGN PRODUCTION
22 | Draft PDP Gallery Asset Briefs | Design Production | Marketing | 3 BD | 2025-06-02 | 2025-06-05 | Final Taglines & Campaign Copy Due (due 2025-06-02) | Single dep: Final Taglines & Campaign Copy Due Due 2025-06-02 → Start → +3BD = 2025-06-05 | PDP gallery image & asset briefs based on final approved taglines/copy.
▸ CONTENT PRODUCTION
23 | Start Sourcing Creators | Content Production | Influencer | 15 BD | 2025-05-19 | 2025-06-09 | Finalize Social Strategy (due 2025-05-19) | Single dep: Finalize Social Strategy Due 2025-05-19 → Start → +15BD = 2025-06-09 | Lead time set to ensure sourcing starts early enough
▸ DESIGN PRODUCTION
24 | 📅 Brief Alignment Meeting | Design Production | Marketing | 3 BD | 2025-06-05 | 2025-06-10 | Draft Email Briefs (due 2025-05-12) Draft PDP Gallery Asset Briefs (due 2025-06-05) Draft Social Creative Briefs (due 2025-05-22) | Waits for ALL 3 deps. Latest dep due: 2025-06-05 Start = 2025-06-05 → Due = +3BD = 2025-06-10 | 📅 Meeting (lead time = scheduling window) Requires ALL 3 draft briefs to be complete before meeting can be scheduled.
▸ CONTENT PRODUCTION
25 | 📅 Creator Review Meeting | Content Production | Influencer | 3 BD | 2025-06-09 | 2025-06-12 | Start Sourcing Creators (due 2025-06-09) | Single dep: Start Sourcing Creators Due 2025-06-09 → Start → +3BD = 2025-06-12 | 📅 Meeting (lead time = scheduling window)
▸ DESIGN PRODUCTION
26 | Asset Design Briefs Due | Design Production | Marketing | 5 BD | 2025-06-10 | 2025-06-17 | Brief Alignment Meeting (due 2025-06-10) | Single dep: Brief Alignment Meeting Due 2025-06-10 → Start → +5BD = 2025-06-17 | Finalized design briefs incorporating alignment meeting feedback.
▸ CONTENT PRODUCTION
27 | Photo Selects Ready | Content Production | Creative | 10 BD | 2025-06-05 | 2025-06-19 | Lifestyle Shoot (due 2025-06-05) Product Shoot (due 2025-06-05) | Waits for ALL 2 deps. Latest dep due: 2025-06-05 Start = 2025-06-05 → Due = +10BD = 2025-06-19 | ~2 weeks for photo selects/retouching from both shoots. These feed into R1 Assets.
28 | Briefs to Creators | Content Production | Influencer | 5 BD | 2025-06-12 | 2025-06-19 | Creator Review Meeting (due 2025-06-12) Samples Available (due 2025-05-15) | Waits for ALL 2 deps. Latest dep due: 2025-06-12 Start = 2025-06-12 → Due = +5BD = 2025-06-19 | Needs BOTH: creator list confirmed (from review meeting) AND product samples ready (to send with briefs).
▸ DESIGN PRODUCTION
29 | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 10 BD | 2025-06-19 | 2025-07-03 | Asset Design Briefs Due (due 2025-06-17) Photo Selects Ready (due 2025-06-19) | Waits for ALL 2 deps. Latest dep due: 2025-06-19 Start = 2025-06-19 → Due = +10BD = 2025-07-03 | First round of all design assets. Requires BOTH: finalized briefs AND photo selects from shoots. ~2 weeks for creative to produce.
30 | Asset Feedback Due | Design Production | Marketing | 3 BD | 2025-07-03 | 2025-07-08 | R1 Assets Due (Email, Social, PDP) (due 2025-07-03) | Single dep: R1 Assets Due (Email, Social, PDP) Due 2025-07-03 → Start → +3BD = 2025-07-08
▸ CONTENT PRODUCTION
31 | Creator Content Delivered | Content Production | Influencer | 15 BD | 2025-06-19 | 2025-07-10 | Briefs to Creators (due 2025-06-19) | Single dep: Briefs to Creators Due 2025-06-19 → Start → +15BD = 2025-07-10
▸ DESIGN PRODUCTION
32 | DTC & Amazon Final Assets Due | Design Production | Creative | 5 BD | 2025-07-08 | 2025-07-15 | Asset Feedback Due (due 2025-07-08) | Single dep: Asset Feedback Due Due 2025-07-08 → Start → +5BD = 2025-07-15 | 🔒 PARTNER ANCHOR (Mattel)
33 | Draft Sephora Catalog & PDP Copy Due | Design Production | Marketing | 5 BD | 2025-07-15 | 2025-07-22 | DTC & Amazon Final Assets Due (due 2025-07-15) | Single dep: DTC & Amazon Final Assets Due Due 2025-07-15 → Start → +5BD = 2025-07-22
34 | Final DTC PDP Copy & Reviews Due | Design Production | Marketing | 3 BD | 2025-07-22 | 2025-07-25 | Draft Sephora Catalog & PDP Copy Due (due 2025-07-22) | Single dep: Draft Sephora Catalog & PDP Copy Due Due 2025-07-22 → Start → +3BD = 2025-07-25
LEGEND
Phase colors: | Green = Content Planning, Yellow = Finalize & Mgmt, Blue = Content Production, Pink = Design Production
🔒 Partner Anchor: | Hard-coded date from external partner (e.g., Mattel). Highest priority — everything schedules around it.
⚠️ Compressed: | Task has less time than its lead time requires. Red highlight = needs attention.
🏪 Channel Anchor: | Task anchored to a specific channel launch date (e.g., Sephora) instead of DTC.
📅 Meeting: | Lead time = scheduling window. Actual meeting is 1 day.
Multi-Dep Rule: | When a task depends on multiple predecessors, it starts after ALL are done (uses the LATEST due date).

## LE Shimmer Lip Oil
LE Shimmer Lip Oil — GTM Schedule
Launch: DTC Aug 6 / Sephora Sep 28 ¦ Start: 2025-05-01 ¦ Total: 69 business days ¦ Tasks: 35
📌 MULTI-DEPENDENCY RULE: When a task has multiple dependencies, it starts after ALL are complete — the scheduler uses the LATEST dependency due date as the starting point.
# | Task Name | Phase | Owner | Lead Time | Start Date | Due Date | Dependencies | Multi-Dep Logic | Flags / Notes
▸ CONTENT PLANNING
1 | Product Sheet & Competitive Landscape | Content Planning | Marketing | 3 BD | 2025-05-01 | 2025-05-06 | — ROOT (no dependencies) | Backward-computed from launch date | First task — start date computed backward from launch date
2 | Draft Product Positioning & Messaging | Content Planning | Marketing | 3 BD | 2025-05-06 | 2025-05-09 | Product Sheet & Competitive Landscape (due 2025-05-06) | Single dep: Product Sheet & Competitive Landscape Due 2025-05-06 → Start → +3BD = 2025-05-09
3 | 📅 GTM Brainstorm Meeting | Content Planning | Marketing | 3 BD | 2025-05-09 | 2025-05-14 | Draft Product Positioning & Messaging (due 2025-05-09) | Single dep: Draft Product Positioning & Messaging Due 2025-05-09 → Start → +3BD = 2025-05-14 | 📅 Meeting (lead time = scheduling window) Align on: positioning, marketing pillars, creative concepts, bundle assortment, retail channel presence
4 | Finalize Product Positioning & Messaging | Content Planning | Marketing | 3 BD | 2025-05-14 | 2025-05-19 | GTM Brainstorm Meeting (due 2025-05-14) | Single dep: GTM Brainstorm Meeting Due 2025-05-14 → Start → +3BD = 2025-05-19
5 | Finalize Creative Shoot Plan | Content Planning | Creative | 3 BD | 2025-05-14 | 2025-05-19 | GTM Brainstorm Meeting (due 2025-05-14) | Single dep: GTM Brainstorm Meeting Due 2025-05-14 → Start → +3BD = 2025-05-19
6 | Finalize Bundle Assortment | Content Planning | Growth | 3 BD | 2025-05-14 | 2025-05-19 | GTM Brainstorm Meeting (due 2025-05-14) | Single dep: GTM Brainstorm Meeting Due 2025-05-14 → Start → +3BD = 2025-05-19
7 | Finalize 360 GTM Plan & Retail Channels | Content Planning | Leadership | 3 BD | 2025-05-14 | 2025-05-19 | GTM Brainstorm Meeting (due 2025-05-14) | Single dep: GTM Brainstorm Meeting Due 2025-05-14 → Start → +3BD = 2025-05-19
8 | Finalize Email Plan | Content Planning | Growth | 3 BD | 2025-05-14 | 2025-05-19 | GTM Brainstorm Meeting (due 2025-05-14) | Single dep: GTM Brainstorm Meeting Due 2025-05-14 → Start → +3BD = 2025-05-19
9 | Submit Tagline + Campaign Copy Brief | Content Planning | Marketing | 3 BD | 2025-05-19 | 2025-05-22 | Finalize Product Positioning & Messaging (due 2025-05-19) | Single dep: Finalize Product Positioning & Messaging Due 2025-05-19 → Start → +3BD = 2025-05-22
▸ FINALIZE & INFORM MGMT
10 | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 3 BD | 2025-05-19 | 2025-05-22 | Finalize Product Positioning & Messaging (due 2025-05-19) Finalize Bundle Assortment (due 2025-05-19) Finalize 360 GTM Plan & Retail Channels (due 2025-05-19) | Waits for ALL 3 deps. Latest dep due: 2025-05-19 Start = 2025-05-19 → Due = +3BD = 2025-05-22 | Align on: final taglines, final 360 GTM plan, bundle assortment. Requires all brainstorm outputs.
▸ DESIGN PRODUCTION
11 | Draft Email Briefs | Design Production | Marketing | 3 BD | 2025-05-19 | 2025-05-22 | Finalize Email Plan (due 2025-05-19) | Single dep: Finalize Email Plan Due 2025-05-19 → Start → +3BD = 2025-05-22 | Email campaign briefs based on finalized email plan from Growth.
▸ CONTENT PRODUCTION
12 | Draft Asset Request Form | Content Production | Marketing | 3 BD | 2025-05-22 | 2025-05-27 | Final GTM Deck (due 2025-05-22) | Single dep: Final GTM Deck Due 2025-05-22 → Start → +3BD = 2025-05-27
13 | Samples Available | Content Production | Ops | 10 BD | 2025-05-13 | 2025-05-27 | — ROOT (no dependencies) | Backward-computed from launch date | Product samples must be physically available 2 weeks (10 BD) before shoots. Due date auto-computed from shoot dates.
▸ CONTENT PLANNING
14 | R1 Taglines & Copy Due | Content Planning | Copywriter | 5 BD | 2025-05-22 | 2025-05-29 | Submit Tagline + Campaign Copy Brief (due 2025-05-22) | Single dep: Submit Tagline + Campaign Copy Brief Due 2025-05-22 → Start → +5BD = 2025-05-29
▸ CONTENT PRODUCTION
15 | Finalize Social Strategy | Content Production | Social | 5 BD | 2025-05-22 | 2025-05-29 | Final GTM Deck (due 2025-05-22) | Single dep: Final GTM Deck Due 2025-05-22 → Start → +5BD = 2025-05-29
▸ DESIGN PRODUCTION
16 | Draft Social Creative Briefs | Design Production | Social | 3 BD | 2025-05-29 | 2025-06-03 | Finalize Social Strategy (due 2025-05-29) | Single dep: Finalize Social Strategy Due 2025-05-29 → Start → +3BD = 2025-06-03 | Social creative direction briefs based on finalized social strategy.
▸ CONTENT PLANNING
17 | Tagline / Copy Iteration | Content Planning | Copywriter | 5 BD | 2025-05-29 | 2025-06-05 | R1 Taglines & Copy Due (due 2025-05-29) | Single dep: R1 Taglines & Copy Due Due 2025-05-29 → Start → +5BD = 2025-06-05
▸ CONTENT PRODUCTION
18 | Finalize Asset Requests | Content Production | Marketing | 10 BD | 2025-05-27 | 2025-06-10 | Draft Asset Request Form (due 2025-05-27) | Single dep: Draft Asset Request Form Due 2025-05-27 → Start → +10BD = 2025-06-10 | Meet with creative during this time to align on all assets needed
▸ CONTENT PLANNING
19 | Final Taglines & Campaign Copy Due | Content Planning | Marketing | 5 BD | 2025-06-05 | 2025-06-12 | Tagline / Copy Iteration (due 2025-06-05) | Single dep: Tagline / Copy Iteration Due 2025-06-05 → Start → +5BD = 2025-06-12
▸ CONTENT PRODUCTION
20 | Lifestyle Shoot | Content Production | Creative | 5 BD | 2025-06-10 | 2025-06-17 | Finalize Asset Requests (due 2025-06-10) Finalize Creative Shoot Plan (due 2025-05-19) Samples Available (due 2025-05-27) | Waits for ALL 3 deps. Latest dep due: 2025-06-10 Start = 2025-06-10 → Due = +5BD = 2025-06-17 | Week-long scheduling window. Depends on: asset requests finalized (what to shoot), creative shoot plan (how to shoot), product samples (what to shoot with).
21 | Product Shoot | Content Production | Creative | 5 BD | 2025-06-10 | 2025-06-17 | Finalize Asset Requests (due 2025-06-10) Finalize Creative Shoot Plan (due 2025-05-19) Samples Available (due 2025-05-27) | Waits for ALL 3 deps. Latest dep due: 2025-06-10 Start = 2025-06-10 → Due = +5BD = 2025-06-17 | Week-long scheduling window. Can run in parallel with or right after Lifestyle Shoot.
▸ DESIGN PRODUCTION
22 | Draft PDP Gallery Asset Briefs | Design Production | Marketing | 3 BD | 2025-06-12 | 2025-06-17 | Final Taglines & Campaign Copy Due (due 2025-06-12) | Single dep: Final Taglines & Campaign Copy Due Due 2025-06-12 → Start → +3BD = 2025-06-17 | PDP gallery image & asset briefs based on final approved taglines/copy.
▸ CONTENT PRODUCTION
23 | Start Sourcing Creators | Content Production | Influencer | 15 BD | 2025-05-29 | 2025-06-19 | Finalize Social Strategy (due 2025-05-29) | Single dep: Finalize Social Strategy Due 2025-05-29 → Start → +15BD = 2025-06-19 | Lead time set to ensure sourcing starts early enough
▸ DESIGN PRODUCTION
24 | 📅 Brief Alignment Meeting | Design Production | Marketing | 3 BD | 2025-06-17 | 2025-06-20 | Draft Email Briefs (due 2025-05-22) Draft PDP Gallery Asset Briefs (due 2025-06-17) Draft Social Creative Briefs (due 2025-06-03) | Waits for ALL 3 deps. Latest dep due: 2025-06-17 Start = 2025-06-17 → Due = +3BD = 2025-06-20 | 📅 Meeting (lead time = scheduling window) Requires ALL 3 draft briefs to be complete before meeting can be scheduled.
▸ CONTENT PRODUCTION
25 | 📅 Creator Review Meeting | Content Production | Influencer | 3 BD | 2025-06-19 | 2025-06-24 | Start Sourcing Creators (due 2025-06-19) | Single dep: Start Sourcing Creators Due 2025-06-19 → Start → +3BD = 2025-06-24 | 📅 Meeting (lead time = scheduling window)
▸ DESIGN PRODUCTION
26 | Asset Design Briefs Due | Design Production | Marketing | 5 BD | 2025-06-20 | 2025-06-27 | Brief Alignment Meeting (due 2025-06-20) | Single dep: Brief Alignment Meeting Due 2025-06-20 → Start → +5BD = 2025-06-27 | Finalized design briefs incorporating alignment meeting feedback.
▸ CONTENT PRODUCTION
27 | Photo Selects Ready | Content Production | Creative | 10 BD | 2025-06-17 | 2025-07-01 | Lifestyle Shoot (due 2025-06-17) Product Shoot (due 2025-06-17) | Waits for ALL 2 deps. Latest dep due: 2025-06-17 Start = 2025-06-17 → Due = +10BD = 2025-07-01 | ~2 weeks for photo selects/retouching from both shoots. These feed into R1 Assets.
28 | Briefs to Creators | Content Production | Influencer | 5 BD | 2025-06-24 | 2025-07-01 | Creator Review Meeting (due 2025-06-24) Samples Available (due 2025-05-27) | Waits for ALL 2 deps. Latest dep due: 2025-06-24 Start = 2025-06-24 → Due = +5BD = 2025-07-01 | Needs BOTH: creator list confirmed (from review meeting) AND product samples ready (to send with briefs).
▸ DESIGN PRODUCTION
29 | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 10 BD | 2025-07-01 | 2025-07-15 | Asset Design Briefs Due (due 2025-06-27) Photo Selects Ready (due 2025-07-01) | Waits for ALL 2 deps. Latest dep due: 2025-07-01 Start = 2025-07-01 → Due = +10BD = 2025-07-15 | First round of all design assets. Requires BOTH: finalized briefs AND photo selects from shoots. ~2 weeks for creative to produce.
30 | Asset Feedback Due | Design Production | Marketing | 3 BD | 2025-07-15 | 2025-07-18 | R1 Assets Due (Email, Social, PDP) (due 2025-07-15) | Single dep: R1 Assets Due (Email, Social, PDP) Due 2025-07-15 → Start → +3BD = 2025-07-18
▸ CONTENT PRODUCTION
31 | Creator Content Delivered | Content Production | Influencer | 15 BD | 2025-07-01 | 2025-07-22 | Briefs to Creators (due 2025-07-01) | Single dep: Briefs to Creators Due 2025-07-01 → Start → +15BD = 2025-07-22
▸ DESIGN PRODUCTION
32 | Sephora Final Assets Due | Design Production | Creative | 5 BD | 2025-07-18 | 2025-07-25 | Asset Feedback Due (due 2025-07-18) | Single dep: Asset Feedback Due Due 2025-07-18 → Start → +5BD = 2025-07-25 | 🏪 Anchored to Sephora launch date
33 | DTC & Amazon Final Assets Due | Design Production | Creative | 5 BD | 2025-07-18 | 2025-07-25 | Asset Feedback Due (due 2025-07-18) | Single dep: Asset Feedback Due Due 2025-07-18 → Start → +5BD = 2025-07-25
34 | Draft Sephora Catalog & PDP Copy Due | Design Production | Marketing | 5 BD | 2025-07-25 | 2025-08-01 | DTC & Amazon Final Assets Due (due 2025-07-25) | Single dep: DTC & Amazon Final Assets Due Due 2025-07-25 → Start → +5BD = 2025-08-01
35 | Final DTC PDP Copy & Reviews Due | Design Production | Marketing | 3 BD | 2025-08-01 | 2025-08-06 | Draft Sephora Catalog & PDP Copy Due (due 2025-08-01) | Single dep: Draft Sephora Catalog & PDP Copy Due Due 2025-08-01 → Start → +3BD = 2025-08-06
LEGEND
Phase colors: | Green = Content Planning, Yellow = Finalize & Mgmt, Blue = Content Production, Pink = Design Production
🔒 Partner Anchor: | Hard-coded date from external partner (e.g., Mattel). Highest priority — everything schedules around it.
⚠️ Compressed: | Task has less time than its lead time requires. Red highlight = needs attention.
🏪 Channel Anchor: | Task anchored to a specific channel launch date (e.g., Sephora) instead of DTC.
📅 Meeting: | Lead time = scheduling window. Actual meeting is 1 day.
Multi-Dep Rule: | When a task depends on multiple predecessors, it starts after ALL are done (uses the LATEST due date).