## Task Reference
Launch Name | Task Name | Phase | Owner | Due Date | Lead Time (days) | Status | Notes / Dependencies
VVIP Ambassador Program | Marketing Positioning | Content Planning | Marketing | 2025-11-07 | 5 | Complete
VVIP Ambassador Program | Tagline/Copy Brief | Content Planning | Marketing | 2025-11-11 | 5 | Complete | Depends on: Marketing Positioning
VVIP Ambassador Program | R1 Taglines | Content Planning | Marketing | 2025-11-13 | 5 | Complete | Depends on: Tagline/Copy Brief
VVIP Ambassador Program | Final Taglines | Content Planning | Marketing | 2025-11-26 | 15 | Complete | Depends on: R1 Taglines (3 weeks R1→Final)
VVIP Ambassador Program | Brainstorm Meeting | Content Planning | Marketing | 2025-11-14 | 1 | Complete
VVIP Ambassador Program | Brainstorm Concepts Approved | Content Planning | Marketing | 2025-11-20 | 3 | Complete | Depends on: Brainstorm Meeting
VVIP Ambassador Program | Asset Request Form | Content Planning | Marketing | 2025-11-21 | 2 | Complete
VVIP Ambassador Program | Draft GTM Deck | Content Planning | Marketing | 2025-11-28 | 5 | Complete | Depends on: Product Sheet, Marketing Positioning done
VVIP Ambassador Program | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2025-12-03 | 3 | Complete | Depends on: Draft GTM Deck
VVIP Ambassador Program | Asset Request Form Approval / AD Start | Content Production | Creative | 2025-12-04 | 2 | Complete | Depends on: Asset Request Form, Final GTM Deck
VVIP Ambassador Program | Photo Sample Ready | Content Production | Creative | 2025-12-12 | 5 | Complete
VVIP Ambassador Program | Lifestyle & Product Shoot | Content Production | Creative | 2025-12-19 | 3 | Complete | Depends on: Photo Sample Ready, Asset Request Form
VVIP Ambassador Program | Samples Available | Content Production | Creative | 2026-02-10 | 5 | Complete
VVIP Ambassador Program | Start Sourcing Creators | Content Production | Influencer | 2026-01-06 | 10 | Complete
VVIP Ambassador Program | Creator Review Meeting | Content Production | Marketing | 2026-01-06 | 1 | Complete | Depends on: Start Sourcing Creators
VVIP Ambassador Program | Briefs to Creators | Content Production | Marketing | 2026-01-27 | 3 | Complete | Depends on: Creator Review Meeting, Samples Available
VVIP Ambassador Program | Creator Content Delivered | Content Production | Creative | 2026-02-17 | 15 | Complete | Depends on: Briefs to Creators (15 BD turnaround)
VVIP Ambassador Program | Brief Alignment Meeting | Design Production | Channel Leads | 2026-01-13 | 1 | Complete
VVIP Ambassador Program | Asset Design Briefs Due | Design Production | Channel Leads | 2026-01-16 | 5 | Complete | Depends on: Brief Alignment Meeting, Final Taglines
VVIP Ambassador Program | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-02-06 | 10 | Complete | Depends on: Asset Design Briefs Due, Photography
VVIP Ambassador Program | Asset Feedback Due | Design Production | Marketing | 2026-02-10 | 3 | Complete | Depends on: R1 Assets Due
VVIP Ambassador Program | DTC Final Assets Due | Design Production | Creative | 2026-02-17 | 5 | Complete | Depends on: Asset Feedback Due (2 wks before DTC launch)
VVIP Ambassador Program | DTC Launch | Design Production | Marketing | 2026-02-24 |  | Complete
Sephora Evereden US In-Store Launch | Marketing Positioning | Content Planning | Marketing | 2025-12-19 | 5 | Complete
Sephora Evereden US In-Store Launch | Tagline/Copy Brief | Content Planning | Marketing | 2025-12-23 | 5 | Complete | Depends on: Marketing Positioning
Sephora Evereden US In-Store Launch | R1 Taglines | Content Planning | Marketing | 2025-12-25 | 5 | Complete | Depends on: Tagline/Copy Brief
Sephora Evereden US In-Store Launch | Final Taglines | Content Planning | Marketing | 2026-02-05 | 15 | Complete | Depends on: R1 Taglines (3 weeks R1→Final)
Sephora Evereden US In-Store Launch | Brainstorm Meeting | Content Planning | Marketing | 2025-12-26 | 1 | Complete
Sephora Evereden US In-Store Launch | Brainstorm Concepts Approved | Content Planning | Marketing | 2026-01-01 | 3 | Complete | Depends on: Brainstorm Meeting
Sephora Evereden US In-Store Launch | Asset Request Form | Content Planning | Marketing | 2026-01-02 | 2 | Complete
Sephora Evereden US In-Store Launch | Draft GTM Deck | Content Planning | Marketing | 2026-02-09 | 5 | Complete | Depends on: Product Sheet, Marketing Positioning done
Sephora Evereden US In-Store Launch | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2026-02-12 | 3 | Complete | Depends on: Draft GTM Deck
Sephora Evereden US In-Store Launch | Samples Available | Content Production | Creative | 2026-03-02 | 5 | Complete
Sephora Evereden US In-Store Launch | Start Sourcing Creators | Content Production | Influencer | 2026-01-06 | 10 | Complete
Sephora Evereden US In-Store Launch | Creator Review Meeting | Content Production | Marketing | 2026-01-26 | 1 | Complete | Depends on: Start Sourcing Creators
Sephora Evereden US In-Store Launch | Briefs to Creators | Content Production | Marketing | 2026-02-16 | 3 | Complete | Depends on: Creator Review Meeting, Samples Available
Sephora Evereden US In-Store Launch | Creator Content Delivered | Content Production | Creative | 2026-03-09 | 15 | Complete | Depends on: Briefs to Creators (15 BD turnaround)
Sephora Evereden US In-Store Launch | Brief Alignment Meeting | Design Production | Channel Leads | 2025-12-15 | 1 | Complete
Sephora Evereden US In-Store Launch | Asset Design Briefs Due | Design Production | Channel Leads | 2025-12-18 | 5 | Complete | Depends on: Brief Alignment Meeting, Final Taglines
Sephora Evereden US In-Store Launch | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-01-08 | 10 | Complete | Depends on: Asset Design Briefs Due, Photography
Sephora Evereden US In-Store Launch | Asset Feedback Due | Design Production | Marketing | 2026-01-12 | 3 | Complete | Depends on: R1 Assets Due
Sephora Evereden US In-Store Launch | Sephora Final Assets Due | Design Production | Creative | 2026-01-19 | 5 | Complete | Depends on: Asset Feedback Due (2 wks before Sephora launch)
Sephora Evereden US In-Store Launch | Sephora Catalog & PDP Copy Due | Design Production | Channel Leads | 2026-01-12 | 5 | Complete | Depends on: Final Taglines
Sephora Evereden US In-Store Launch | Sephora US Launch | Design Production | Retail | 2026-03-16 |  | Complete
Sephora Evereden US In-Store Launch | DTC Launch | Design Production | Marketing | 2026-03-16 |  | Complete
LE Fragrance Mist x Embreigh | Marketing Positioning | Content Planning | Marketing | 2026-01-16 | 5 | Complete
LE Fragrance Mist x Embreigh | Tagline/Copy Brief | Content Planning | Marketing | 2026-01-20 | 5 | Complete | Depends on: Marketing Positioning
LE Fragrance Mist x Embreigh | R1 Taglines | Content Planning | Marketing | 2026-01-22 | 5 | Complete | Depends on: Tagline/Copy Brief
LE Fragrance Mist x Embreigh | Final Taglines | Content Planning | Marketing | 2026-02-04 | 15 | Complete | Depends on: R1 Taglines (3 weeks R1→Final)
LE Fragrance Mist x Embreigh | Brainstorm Meeting | Content Planning | Marketing | 2026-01-23 | 1 | Complete
LE Fragrance Mist x Embreigh | Brainstorm Concepts Approved | Content Planning | Marketing | 2026-01-29 | 3 | Complete | Depends on: Brainstorm Meeting
LE Fragrance Mist x Embreigh | Asset Request Form | Content Planning | Marketing | 2026-01-30 | 2 | Complete
LE Fragrance Mist x Embreigh | Draft GTM Deck | Content Planning | Marketing | 2026-02-06 | 5 | Complete | Depends on: Product Sheet, Marketing Positioning done
LE Fragrance Mist x Embreigh | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2026-02-11 | 3 | Complete | Depends on: Draft GTM Deck
LE Fragrance Mist x Embreigh | Asset Request Form Approval / AD Start | Content Production | Creative | 2026-02-12 | 2 | Complete | Depends on: Asset Request Form, Final GTM Deck
LE Fragrance Mist x Embreigh | Photo Sample Ready | Content Production | Creative | 2026-02-20 | 5 | Complete
LE Fragrance Mist x Embreigh | Lifestyle & Product Shoot | Content Production | Creative | 2026-02-27 | 3 | Complete | Depends on: Photo Sample Ready, Asset Request Form
LE Fragrance Mist x Embreigh | Samples Available | Content Production | Creative | 2026-04-21 | 5 | Not Started
LE Fragrance Mist x Embreigh | Start Sourcing Creators | Content Production | Influencer | 2026-02-25 | 10 | Complete
LE Fragrance Mist x Embreigh | Creator Review Meeting | Content Production | Marketing | 2026-03-17 | 1 | Complete | Depends on: Start Sourcing Creators
LE Fragrance Mist x Embreigh | Briefs to Creators | Content Production | Marketing | 2026-04-07 | 3 | Not Started | Depends on: Creator Review Meeting, Samples Available
LE Fragrance Mist x Embreigh | Creator Content Delivered | Content Production | Creative | 2026-04-28 | 15 | Not Started | Depends on: Briefs to Creators (15 BD turnaround)
LE Fragrance Mist x Embreigh | Brief Alignment Meeting | Design Production | Channel Leads | 2026-03-24 | 1 | Complete
LE Fragrance Mist x Embreigh | Asset Design Briefs Due | Design Production | Channel Leads | 2026-03-27 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
LE Fragrance Mist x Embreigh | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-04-17 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
LE Fragrance Mist x Embreigh | Asset Feedback Due | Design Production | Marketing | 2026-04-21 | 3 | Not Started | Depends on: R1 Assets Due
LE Fragrance Mist x Embreigh | DTC Final Assets Due | Design Production | Creative | 2026-04-28 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before DTC launch)
LE Fragrance Mist x Embreigh | DTC Launch | Design Production | Marketing | 2026-05-05 |  | Not Started
Kids Cooling Mineral Sunstick SPF30 | Marketing Positioning | Content Planning | Marketing | 2026-02-18 | 5 | Complete
Kids Cooling Mineral Sunstick SPF30 | Tagline/Copy Brief | Content Planning | Marketing | 2026-02-20 | 5 | Complete | Depends on: Marketing Positioning
Kids Cooling Mineral Sunstick SPF30 | R1 Taglines | Content Planning | Marketing | 2026-02-24 | 5 | Complete | Depends on: Tagline/Copy Brief
Kids Cooling Mineral Sunstick SPF30 | Final Taglines | Content Planning | Marketing | 2026-03-12 | 15 | Complete | Depends on: R1 Taglines (3 weeks R1→Final)
Kids Cooling Mineral Sunstick SPF30 | Brainstorm Meeting | Content Planning | Marketing | 2026-02-25 | 1 | Complete
Kids Cooling Mineral Sunstick SPF30 | Brainstorm Concepts Approved | Content Planning | Marketing | 2026-03-20 | 3 | Complete | Depends on: Brainstorm Meeting
Kids Cooling Mineral Sunstick SPF30 | Asset Request Form | Content Planning | Marketing | 2026-03-23 | 2 | Complete
Kids Cooling Mineral Sunstick SPF30 | Draft GTM Deck | Content Planning | Marketing | 2026-03-30 | 5 | Not Started | Depends on: Product Sheet, Marketing Positioning done
Kids Cooling Mineral Sunstick SPF30 | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2026-04-02 | 3 | Not Started | Depends on: Draft GTM Deck
Kids Cooling Mineral Sunstick SPF30 | Asset Request Form Approval / AD Start | Content Production | Creative | 2026-04-03 | 2 | Not Started | Depends on: Asset Request Form, Final GTM Deck
Kids Cooling Mineral Sunstick SPF30 | Photo Sample Ready | Content Production | Creative | 2026-04-13 | 5 | Not Started
Kids Cooling Mineral Sunstick SPF30 | Lifestyle & Product Shoot | Content Production | Creative | 2026-04-18 | 3 | Not Started | Depends on: Photo Sample Ready, Asset Request Form
Kids Cooling Mineral Sunstick SPF30 | Start Sourcing Creators | Content Production | Influencer | 2026-03-18 | 10 | Complete
Kids Cooling Mineral Sunstick SPF30 | Creator Review Meeting | Content Production | Marketing | 2026-04-07 | 1 | Not Started | Depends on: Start Sourcing Creators
Kids Cooling Mineral Sunstick SPF30 | Briefs to Creators | Content Production | Marketing | 2026-04-21 | 3 | Not Started | Depends on: Creator Review Meeting, Samples Available
Kids Cooling Mineral Sunstick SPF30 | Creator Content Delivered | Content Production | Creative | 2026-05-12 | 15 | Not Started | Depends on: Briefs to Creators (15 BD turnaround)
Kids Cooling Mineral Sunstick SPF30 | Brief Alignment Meeting | Design Production | Channel Leads | 2026-04-07 | 1 | Not Started
Kids Cooling Mineral Sunstick SPF30 | Asset Design Briefs Due | Design Production | Channel Leads | 2026-04-10 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
Kids Cooling Mineral Sunstick SPF30 | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-05-01 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
Kids Cooling Mineral Sunstick SPF30 | Asset Feedback Due | Design Production | Marketing | 2026-05-05 | 3 | Not Started | Depends on: R1 Assets Due
Kids Cooling Mineral Sunstick SPF30 | Sephora Final Assets Due | Design Production | Creative | 2026-05-12 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before Sephora launch)
Kids Cooling Mineral Sunstick SPF30 | DTC Final Assets Due | Design Production | Creative | 2026-05-12 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before DTC launch)
Kids Cooling Mineral Sunstick SPF30 | Sephora Catalog & PDP Copy Due | Design Production | Channel Leads | 2026-04-28 | 5 | Not Started | Depends on: Final Taglines
Kids Cooling Mineral Sunstick SPF30 | DTC PDP Copy & Reviews Due | Design Production | Channel Leads | 2026-04-28 | 3 | Not Started | Depends on: Final Taglines
Kids Cooling Mineral Sunstick SPF30 | DTC Launch | Design Production | Marketing | 2026-05-19 |  | Not Started
Kids Cooling Mineral Sunstick SPF30 | Sephora US Launch | Design Production | Retail | 2026-06-30 |  | Not Started
Kids Deodorant | Marketing Positioning | Content Planning | Marketing | 2026-03-09 | 5 | Complete
Kids Deodorant | Tagline/Copy Brief | Content Planning | Marketing | 2026-03-11 | 5 | Complete | Depends on: Marketing Positioning
Kids Deodorant | R1 Taglines | Content Planning | Marketing | 2026-03-13 | 5 | Complete | Depends on: Tagline/Copy Brief
Kids Deodorant | Final Taglines | Content Planning | Marketing | 2026-03-26 | 15 | Complete | Depends on: R1 Taglines (3 weeks R1→Final)
Kids Deodorant | Brainstorm Meeting | Content Planning | Marketing | 2026-03-16 | 1 | Complete
Kids Deodorant | Brainstorm Concepts Approved | Content Planning | Marketing | 2026-03-20 | 3 | Complete | Depends on: Brainstorm Meeting
Kids Deodorant | Asset Request Form | Content Planning | Marketing | 2026-03-23 | 2 | Complete
Kids Deodorant | Draft GTM Deck | Content Planning | Marketing | 2026-03-30 | 5 | Not Started | Depends on: Product Sheet, Marketing Positioning done
Kids Deodorant | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2026-04-02 | 3 | Not Started | Depends on: Draft GTM Deck
Kids Deodorant | Asset Request Form Approval / AD Start | Content Production | Creative | 2026-04-03 | 2 | Not Started | Depends on: Asset Request Form, Final GTM Deck
Kids Deodorant | Photo Sample Ready | Content Production | Creative | 2026-04-13 | 5 | Not Started
Kids Deodorant | Lifestyle & Product Shoot | Content Production | Creative | 2026-04-18 | 3 | Not Started | Depends on: Photo Sample Ready, Asset Request Form
Kids Deodorant | Samples Available | Content Production | Creative | 2026-06-05 | 5 | Not Started
Kids Deodorant | Start Sourcing Creators | Content Production | Influencer | 2026-04-13 | 10 | Not Started
Kids Deodorant | Creator Review Meeting | Content Production | Marketing | 2026-05-01 | 1 | Not Started | Depends on: Start Sourcing Creators
Kids Deodorant | Briefs to Creators | Content Production | Marketing | 2026-05-22 | 3 | Not Started | Depends on: Creator Review Meeting, Samples Available
Kids Deodorant | Creator Content Delivered | Content Production | Creative | 2026-06-12 | 15 | Not Started | Depends on: Briefs to Creators (15 BD turnaround)
Kids Deodorant | Brief Alignment Meeting | Design Production | Channel Leads | 2026-04-10 | 1 | Not Started
Kids Deodorant | Asset Design Briefs Due | Design Production | Channel Leads | 2026-04-15 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
Kids Deodorant | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-05-06 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
Kids Deodorant | Asset Feedback Due | Design Production | Marketing | 2026-05-08 | 3 | Not Started | Depends on: R1 Assets Due
Kids Deodorant | Sephora Final Assets Due | Design Production | Creative | 2026-05-15 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before Sephora launch)
Kids Deodorant | DTC Final Assets Due | Design Production | Creative | 2026-06-12 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before DTC launch)
Kids Deodorant | Sephora Catalog & PDP Copy Due | Design Production | Channel Leads | 2026-05-29 | 5 | Not Started | Depends on: Final Taglines
Kids Deodorant | DTC PDP Copy & Reviews Due | Design Production | Channel Leads | 2026-05-01 | 3 | Not Started | Depends on: Final Taglines
Kids Deodorant | DTC Launch | Design Production | Marketing | 2026-06-19 |  | Not Started
Kids Deodorant | Sephora US Launch | Design Production | Retail | 2026-07-03 |  | Not Started
Polly Pocket Set | Marketing Positioning | Content Planning | Marketing | 2026-03-11 | 5 | Complete
Polly Pocket Set | Tagline/Copy Brief | Content Planning | Marketing | 2026-03-06 | 5 | Complete | Depends on: Marketing Positioning
Polly Pocket Set | R1 Taglines | Content Planning | Marketing | 2026-03-17 | 5 | Complete | Depends on: Tagline/Copy Brief
Polly Pocket Set | Final Taglines | Content Planning | Marketing | 2026-03-31 | 15 | Not Started | Depends on: R1 Taglines (3 weeks R1→Final)
Polly Pocket Set | Brainstorm Meeting | Content Planning | Marketing | 2026-03-18 | 1 | Complete
Polly Pocket Set | Brainstorm Concepts Approved | Content Planning | Marketing | 2026-03-20 | 3 | Complete | Depends on: Brainstorm Meeting
Polly Pocket Set | Asset Request Form | Content Planning | Marketing | 2026-03-23 | 2 | Complete
Polly Pocket Set | Draft GTM Deck | Content Planning | Marketing | 2026-03-30 | 5 | Not Started | Depends on: Product Sheet, Marketing Positioning done
Polly Pocket Set | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2026-04-02 | 3 | Not Started | Depends on: Draft GTM Deck
Polly Pocket Set | Asset Request Form Approval / AD Start | Content Production | Creative | 2026-04-20 | 2 | Not Started | Depends on: Asset Request Form, Final GTM Deck
Polly Pocket Set | Photo Sample Ready | Content Production | Creative | 2026-05-04 | 5 | Not Started
Polly Pocket Set | Lifestyle & Product Shoot | Content Production | Creative | 2026-05-11 | 3 | Not Started | Depends on: Photo Sample Ready, Asset Request Form
Polly Pocket Set | Samples Available | Content Production | Creative | 2026-06-01 | 5 | Not Started
Polly Pocket Set | Start Sourcing Creators | Content Production | Influencer | 2026-04-20 | 10 | Not Started
Polly Pocket Set | Creator Review Meeting | Content Production | Marketing | 2026-05-11 | 1 | Not Started | Depends on: Start Sourcing Creators
Polly Pocket Set | Briefs to Creators | Content Production | Marketing | 2026-06-01 | 3 | Not Started | Depends on: Creator Review Meeting, Samples Available
Polly Pocket Set | Creator Content Delivered | Content Production | Creative | 2026-07-03 | 15 | Not Started | Depends on: Briefs to Creators (15 BD turnaround)
Polly Pocket Set | Brief Alignment Meeting | Design Production | Channel Leads | 2026-06-03 | 1 | Not Started
Polly Pocket Set | Asset Design Briefs Due | Design Production | Channel Leads | 2026-06-08 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
Polly Pocket Set | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-07-06 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
Polly Pocket Set | Asset Feedback Due | Design Production | Marketing | 2026-07-24 | 3 | Not Started | Depends on: R1 Assets Due
Polly Pocket Set | DTC Final Assets Due | Design Production | Creative | 2026-07-28 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before DTC launch)
Polly Pocket Set | DTC Launch | Design Production | Marketing | 2026-08-04 |  | Not Started
LE Shimmer Lip Oil | Marketing Positioning | Content Planning | Marketing | 2026-03-25 | 5 | Not Started
LE Shimmer Lip Oil | Tagline/Copy Brief | Content Planning | Marketing | 2026-03-27 | 5 | Not Started | Depends on: Marketing Positioning
LE Shimmer Lip Oil | R1 Taglines | Content Planning | Marketing | 2026-03-31 | 5 | Not Started | Depends on: Tagline/Copy Brief
LE Shimmer Lip Oil | Final Taglines | Content Planning | Marketing | 2026-04-13 | 15 | Not Started | Depends on: R1 Taglines (3 weeks R1→Final)
LE Shimmer Lip Oil | Brainstorm Meeting | Content Planning | Marketing | 2026-04-01 | 1 | Not Started
LE Shimmer Lip Oil | Brainstorm Concepts Approved | Content Planning | Marketing | 2026-04-07 | 3 | Not Started | Depends on: Brainstorm Meeting
LE Shimmer Lip Oil | Asset Request Form | Content Planning | Marketing | 2026-04-08 | 2 | Not Started
LE Shimmer Lip Oil | Draft GTM Deck | Content Planning | Marketing | 2026-04-15 | 5 | Not Started | Depends on: Product Sheet, Marketing Positioning done
LE Shimmer Lip Oil | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2026-04-18 | 3 | Not Started | Depends on: Draft GTM Deck
LE Shimmer Lip Oil | Asset Request Form Approval / AD Start | Content Production | Creative | 2026-05-20 | 2 | Not Started | Depends on: Asset Request Form, Final GTM Deck
LE Shimmer Lip Oil | Photo Sample Ready | Content Production | Creative | 2026-05-28 | 5 | Not Started
LE Shimmer Lip Oil | Lifestyle & Product Shoot | Content Production | Creative | 2026-06-04 | 3 | Not Started | Depends on: Photo Sample Ready, Asset Request Form
LE Shimmer Lip Oil | Samples Available | Content Production | Creative | 2026-07-23 | 5 | Not Started
LE Shimmer Lip Oil | Start Sourcing Creators | Content Production | Influencer | 2026-05-29 | 10 | Not Started
LE Shimmer Lip Oil | Creator Review Meeting | Content Production | Marketing | 2026-06-18 | 1 | Not Started | Depends on: Start Sourcing Creators
LE Shimmer Lip Oil | Briefs to Creators | Content Production | Marketing | 2026-07-09 | 3 | Not Started | Depends on: Creator Review Meeting, Samples Available
LE Shimmer Lip Oil | Creator Content Delivered | Content Production | Creative | 2026-07-30 | 15 | Not Started | Depends on: Briefs to Creators (15 BD turnaround)
LE Shimmer Lip Oil | Brief Alignment Meeting | Design Production | Channel Leads | 2026-06-29 | 1 | Not Started
LE Shimmer Lip Oil | Asset Design Briefs Due | Design Production | Channel Leads | 2026-07-02 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
LE Shimmer Lip Oil | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-07-23 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
LE Shimmer Lip Oil | Asset Feedback Due | Design Production | Marketing | 2026-07-27 | 3 | Not Started | Depends on: R1 Assets Due
LE Shimmer Lip Oil | Sephora Final Assets Due | Design Production | Creative | 2026-08-03 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before Sephora launch)
LE Shimmer Lip Oil | DTC Final Assets Due | Design Production | Creative | 2026-07-30 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before DTC launch)
LE Shimmer Lip Oil | Sephora Catalog & PDP Copy Due | Design Production | Channel Leads | 2026-07-16 | 5 | Not Started | Depends on: Final Taglines
LE Shimmer Lip Oil | DTC PDP Copy & Reviews Due | Design Production | Channel Leads | 2026-07-27 | 3 | Not Started | Depends on: Final Taglines
LE Shimmer Lip Oil | DTC Launch | Design Production | Marketing | 2026-08-06 |  | Not Started
LE Shimmer Lip Oil | Sephora US Launch | Design Production | Retail | 2026-09-28 |  | Not Started
Sephora Evergreen Set | Brief Alignment Meeting | Design Production | Channel Leads | 2026-06-29 | 1 | Not Started
Sephora Evergreen Set | Asset Design Briefs Due | Design Production | Channel Leads | 2026-07-02 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
Sephora Evergreen Set | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-07-23 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
Sephora Evergreen Set | Asset Feedback Due | Design Production | Marketing | 2026-07-27 | 3 | Not Started | Depends on: R1 Assets Due
Sephora Evergreen Set | Sephora Final Assets Due | Design Production | Creative | 2026-08-03 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before Sephora launch)
Sephora Evergreen Set | Sephora Catalog & PDP Copy Due | Design Production | Channel Leads | 2026-07-13 | 5 | Not Started | Depends on: Final Taglines
Sephora Evergreen Set | Sephora US Launch | Design Production | Retail | 2026-09-28 |  | Not Started
Kaili Holiday Set | Marketing Positioning | Content Planning | Marketing | 2026-06-12 | 5 | Not Started
Kaili Holiday Set | Tagline/Copy Brief | Content Planning | Marketing | 2026-06-16 | 5 | Not Started | Depends on: Marketing Positioning
Kaili Holiday Set | R1 Taglines | Content Planning | Marketing | 2026-06-18 | 5 | Not Started | Depends on: Tagline/Copy Brief
Kaili Holiday Set | Final Taglines | Content Planning | Marketing | 2026-07-01 | 15 | Not Started | Depends on: R1 Taglines (3 weeks R1→Final)
Kaili Holiday Set | Brainstorm Meeting | Content Planning | Marketing | 2026-06-19 | 1 | Not Started
Kaili Holiday Set | Brainstorm Concepts Approved | Content Planning | Marketing | 2026-06-25 | 3 | Not Started | Depends on: Brainstorm Meeting
Kaili Holiday Set | Asset Request Form | Content Planning | Marketing | 2026-06-26 | 2 | Not Started
Kaili Holiday Set | Draft GTM Deck | Content Planning | Marketing | 2026-07-03 | 5 | Not Started | Depends on: Product Sheet, Marketing Positioning done
Kaili Holiday Set | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2026-07-08 | 3 | Not Started | Depends on: Draft GTM Deck
Kaili Holiday Set | Asset Request Form Approval / AD Start | Content Production | Creative | 2026-07-09 | 2 | Not Started | Depends on: Asset Request Form, Final GTM Deck
Kaili Holiday Set | Photo Sample Ready | Content Production | Creative | 2026-07-17 | 5 | Not Started
Kaili Holiday Set | Lifestyle & Product Shoot | Content Production | Creative | 2026-07-24 | 3 | Not Started | Depends on: Photo Sample Ready, Asset Request Form
Kaili Holiday Set | Samples Available | Content Production | Creative | 2026-09-15 | 5 | Not Started
Kaili Holiday Set | Start Sourcing Creators | Content Production | Influencer | 2026-08-11 | 10 | Not Started
Kaili Holiday Set | Creator Review Meeting | Content Production | Marketing | 2026-08-11 | 1 | Not Started | Depends on: Start Sourcing Creators
Kaili Holiday Set | Briefs to Creators | Content Production | Marketing | 2026-09-01 | 3 | Not Started | Depends on: Creator Review Meeting, Samples Available
Kaili Holiday Set | Creator Content Delivered | Content Production | Creative | 2026-09-22 | 15 | Not Started | Depends on: Briefs to Creators (15 BD turnaround)
Kaili Holiday Set | Brief Alignment Meeting | Design Production | Channel Leads | 2026-08-18 | 1 | Not Started
Kaili Holiday Set | Asset Design Briefs Due | Design Production | Channel Leads | 2026-08-21 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
Kaili Holiday Set | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-09-11 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
Kaili Holiday Set | Asset Feedback Due | Design Production | Marketing | 2026-09-15 | 3 | Not Started | Depends on: R1 Assets Due
Kaili Holiday Set | DTC Final Assets Due | Design Production | Creative | 2026-09-22 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before DTC launch)
Kaili Holiday Set | Sephora Catalog & PDP Copy Due | Design Production | Channel Leads | 2026-09-08 | 5 | Not Started | Depends on: Final Taglines
Kaili Holiday Set | DTC Launch | Design Production | Marketing | 2026-09-29 |  | Not Started
Embreigh Holiday Set | Marketing Positioning | Content Planning | Marketing | 2026-06-19 | 5 | Not Started
Embreigh Holiday Set | Tagline/Copy Brief | Content Planning | Marketing | 2026-06-23 | 5 | Not Started | Depends on: Marketing Positioning
Embreigh Holiday Set | R1 Taglines | Content Planning | Marketing | 2026-06-25 | 5 | Not Started | Depends on: Tagline/Copy Brief
Embreigh Holiday Set | Final Taglines | Content Planning | Marketing | 2026-07-08 | 15 | Not Started | Depends on: R1 Taglines (3 weeks R1→Final)
Embreigh Holiday Set | Brainstorm Meeting | Content Planning | Marketing | 2026-06-26 | 1 | Not Started
Embreigh Holiday Set | Brainstorm Concepts Approved | Content Planning | Marketing | 2026-07-02 | 3 | Not Started | Depends on: Brainstorm Meeting
Embreigh Holiday Set | Asset Request Form | Content Planning | Marketing | 2026-07-03 | 2 | Not Started
Embreigh Holiday Set | Draft GTM Deck | Content Planning | Marketing | 2026-07-10 | 5 | Not Started | Depends on: Product Sheet, Marketing Positioning done
Embreigh Holiday Set | Final GTM Deck | Finalize & Inform Mgmt | Marketing | 2026-07-15 | 3 | Not Started | Depends on: Draft GTM Deck
Embreigh Holiday Set | Asset Request Form Approval / AD Start | Content Production | Creative | 2026-07-16 | 2 | Not Started | Depends on: Asset Request Form, Final GTM Deck
Embreigh Holiday Set | Photo Sample Ready | Content Production | Creative | 2026-07-24 | 5 | Not Started
Embreigh Holiday Set | Lifestyle & Product Shoot | Content Production | Creative | 2026-07-31 | 3 | Not Started | Depends on: Photo Sample Ready, Asset Request Form
Embreigh Holiday Set | Samples Available | Content Production | Creative | 2026-09-22 | 5 | Not Started
Embreigh Holiday Set | Start Sourcing Creators | Content Production | Influencer | 2026-08-18 | 10 | Not Started
Embreigh Holiday Set | Creator Review Meeting | Content Production | Marketing | 2026-08-18 | 1 | Not Started | Depends on: Start Sourcing Creators
Embreigh Holiday Set | Briefs to Creators | Content Production | Marketing | 2026-09-08 | 3 | Not Started | Depends on: Creator Review Meeting, Samples Available
Embreigh Holiday Set | Creator Content Delivered | Content Production | Creative | 2026-09-29 | 15 | Not Started | Depends on: Briefs to Creators (15 BD turnaround)
Embreigh Holiday Set | Brief Alignment Meeting | Design Production | Channel Leads | 2026-08-25 | 1 | Not Started
Embreigh Holiday Set | Asset Design Briefs Due | Design Production | Channel Leads | 2026-08-28 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
Embreigh Holiday Set | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-09-18 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
Embreigh Holiday Set | Asset Feedback Due | Design Production | Marketing | 2026-09-22 | 3 | Not Started | Depends on: R1 Assets Due
Embreigh Holiday Set | DTC Final Assets Due | Design Production | Creative | 2026-09-29 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before DTC launch)
Embreigh Holiday Set | Sephora Catalog & PDP Copy Due | Design Production | Channel Leads | 2026-09-15 | 5 | Not Started | Depends on: Final Taglines
Embreigh Holiday Set | DTC Launch | Design Production | Marketing | 2026-10-06 |  | Not Started
Teen Holiday Set | Asset Design Briefs Due | Design Production | Channel Leads | 2026-07-07 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
Teen Holiday Set | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-07-28 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
Teen Holiday Set | Asset Feedback Due | Design Production | Marketing | 2026-07-30 | 3 | Not Started | Depends on: R1 Assets Due
Teen Holiday Set | Sephora Final Assets Due | Design Production | Creative | 2026-08-03 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before Sephora launch)
Teen Holiday Set | DTC Final Assets Due | Design Production | Creative | 2026-09-29 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before DTC launch)
Teen Holiday Set | Sephora Catalog & PDP Copy Due | Design Production | Channel Leads | 2026-09-15 | 5 | Not Started | Depends on: Final Taglines
Teen Holiday Set | DTC PDP Copy & Reviews Due | Design Production | Channel Leads | 2026-07-27 | 3 | Not Started | Depends on: Final Taglines
Teen Holiday Set | Sephora US Launch | Design Production | Retail | 2026-09-28 |  | Not Started
Teen Holiday Set | DTC Launch | Design Production | Marketing | 2026-10-06 |  | Not Started
Preppy in Pink Holiday Set | Asset Design Briefs Due | Design Production | Channel Leads | 2026-07-07 | 5 | Not Started | Depends on: Brief Alignment Meeting, Final Taglines
Preppy in Pink Holiday Set | R1 Assets Due (Email, Social, PDP) | Design Production | Creative | 2026-07-28 | 10 | Not Started | Depends on: Asset Design Briefs Due, Photography
Preppy in Pink Holiday Set | Asset Feedback Due | Design Production | Marketing | 2026-07-30 | 3 | Not Started | Depends on: R1 Assets Due
Preppy in Pink Holiday Set | Sephora Final Assets Due | Design Production | Creative | 2026-08-03 | 5 | Not Started | Depends on: Asset Feedback Due (2 wks before Sephora launch)
Preppy in Pink Holiday Set | DTC PDP Copy & Reviews Due | Design Production | Channel Leads | 2026-07-27 | 3 | Not Started | Depends on: Final Taglines
Preppy in Pink Holiday Set | Sephora US Launch | Design Production | Retail | 2026-09-28 |  | Not Started

## Launch Overview
Launch Name | Tier | Launch Type | DTC Launch | Sephora Launch | Amazon Launch | Category | Status | Total Tasks | Description
VVIP Ambassador Program | A | Campaign / Moment | 2026-02-24 |  |  | Brand | Launched | 23 | VIP ambassador program launch with full content production
Sephora Evereden US In-Store Launch | A | New Product Launch | 2026-03-16 | 2026-03-16 |  | Retail | Launched | 22 | Sephora US in-store launch
LE Fragrance Mist x Embreigh | A | Collaboration | 2026-05-05 |  |  | Kids | In Progress | 23 | Limited edition fragrance mist collaboration with Embreigh
Kids Cooling Mineral Sunstick SPF30 | B | New Product Launch | 2026-05-19 | 2026-06-30 |  | Kids | In Progress | 26 | New SPF30 mineral sunstick for kids
Kids Deodorant | A | New Product Launch | 2026-06-19 | 2026-07-03 |  | Kids | In Progress | 27 | New category entry — kids deodorant
Polly Pocket Set | A | Collaboration | 2026-08-04 |  |  | Kids | In Progress | 23 | Polly Pocket x Evereden collaboration set
LE Shimmer Lip Oil | B | New Product Launch | 2026-08-06 | 2026-09-28 |  | Kids | Planning | 27 | Limited edition shimmer lip oil
Sephora Evergreen Set | B | Seasonal | 2026-09-28 | 2026-09-28 |  | Retail | Planning | 7 | Sephora evergreen set — design production only
Kaili Holiday Set | B | Seasonal | 2026-09-29 |  |  | Kids | Planning | 24 | Kaili holiday gift set with full production
Embreigh Holiday Set | B | Seasonal | 2026-10-06 |  |  | Kids | Planning | 24 | Embreigh holiday gift set with full production
Teen Holiday Set | B | Seasonal | 2026-10-06 | 2026-09-28 |  | Teen | Planning | 9 | Teen holiday set — design production only
Preppy in Pink Holiday Set | B | Seasonal | 2026-09-28 | 2026-09-28 |  | Kids | Planning | 6 | Preppy in Pink holiday set — Sephora exclusive

## Lead Times Reference
Task Name | Lead Time (Business Days) | Dependent On | Typical Phase | Notes | Owner | Support
Launch Date |  | nothing |  | need to be able to set this date and have everything work from there
Product Sheet & Competitive Landscape | 3 | Launch Date | GTM Planning | start date should be based on the launch date | Marketing | Marketing
Draft Product Positioning Positioning & Messaging Pillars | 3 | Product Sheet & Competitive Landscape | GTM Planning |  | Marketing | Marketing
GTM Brainstorm Meeting | 3 | Draft Product Positioning Positioning & Messaging Pillars | Cross-functional Alignment | NEED TO ALIGN ON: Positioning, marketing pillars, high-level shoot plan (creative direction, models, imagery concepting to inform campaign messaging), bundles, high-level 360 GTM plan (# emails, social takeover caliber, paid vs organic influencer/UGC, paid ads, events, OOH), retail channels (d2c, amazon, sephora, SECA) | Marketing | cross-functional
Finalize Product Positioning Positioning & Messaging Pillars | 3 | GTM Brainstorm Meeting |  |  | Marketing
Finalize Creative Shoot Plan | 3 | GTM Brainstorm Meeting |  |  | creative
Finalize Bundle Assortment | 3 | GTM Brainstorm Meeting |  |  | growth
Finalize 360 GTM Plan & Retail Channels | 3 | GTM Brainstorm Meeting |  |  | leadership
Set Up Event Planning Meeting (if appl.) | 10 | Launch Event |  | giving 2 weeks to start working on that | Marketing
Set Up OOH Planning (if appl.) | 10 | OOH Campaign |  | giving 2 weeks to start working on that | Marketing
Submit Tagline + Campaign Copy Brief | 3 | Finalize Product Positioning Positioning & Messaging Pillars | Content Planning |  | Marketing | Copywriter
R1 Taglines & Copy Due | 5 | Submit Tagline + Campaign Copy Brief | Content Planning |  | Copywriter
Tagline / Copy Iteration | 5 | R1 Taglines & Copy Due |  |  | Copywriter
Final Taglines & Campaign Copy Due | 5 | Tagline / Copy Iteration | Content Planning |  | Marketing | Copywriter
Draft Asset Request Form | 3 | Final GTM Deck | Content Planning |  | Marketing | Creative
Final GTM Deck | 3 | Finalize Product Positioning Positioning & Messaging Pillars Finalize Creative Shoot Plan Finalize Bundle Assortment Finalize 360 GTM Plan & Retail Channels | Finalize & Inform Mgmt | NEED TO ALIGN ON: Final taglines, final 360 GTM plan, final creative shoot/campaign, final bundles | Marketing | cross-functional
Finalize social strategy | 5 | Final GTM Deck |  |  | Social
Finalize Asset Requests | 10 | Draft Asset Request Form | Content Production | Meet with creative during this time to align if needed, esp on video content or unique shoots | Marketing | Creative
Lifestyle Shoot | should be a week-long window for scheduling, need to have finalized asset requests and needs to give about 2 weeks for us to get samples of the lifestyle images and about 2 more weeks for creative to create the R1 assets | Finalize Asset Requests R1 Assets Due | Content Production | need to create an integration option to change this date and have the following dates and dependencies adjust accordingly if we don’t have packaging samples in time or need to combine shoots or something | Creative
Product Shoot | should be a week-long window for scheduling, need to have finalized asset requests and needs to give about 2 weeks for us to get samples of the lifestyle images and about 2 more weeks for creative to create the R1 assets | Finalize Asset Requests R1 Assets Due | Content Production | need to create an integration option to change this date and have the following dates and dependencies adjust accordingly if we don’t have packaging samples in time or need to combine shoots or something | Creative
Samples Available | -10 | Lifestyle Shoot Product Shoot | Content Production | samples need to be available two weeks before both of these shoots. So date should be 10 days before whichever one is earlier | ops | Creative
Start Sourcing Creators | 15 | Finalize social strategy | Content Production | this doesn't take 15 days I just did that so theres more time til it needs to be started like we don’t need to source creators until closer to launch | Influencer
Creator Review Meeting | 3 | Start Sourcing Creators | Content Production |  | Influencer
Briefs to Creators | 5 | Creator Review Meeting Samples Available | Content Production |  | Influencer
Creator Content Delivered | 15 | Briefs to Creators | Content Production |  | Influencer
Brief Alignment Meeting | 3 | Final Taglines & Campaign Copy Due | Design Production |  | Marketing
Asset Design Briefs Due | 5 | Brief Alignment Meeting | Design Production |  | Marketing
R1 Assets Due (Email, Social, PDP) | 10 | Asset Design Briefs Due | Design Production |  | creative
Asset Feedback Due | 3 | R1 Assets Due (Email, Social, PDP) | Design Production |  | Marketing
Sephora Final Assets Due | 5 | Asset Feedback Due | Design Production |  | Creative
DTC & Amazon Final Assets Due | 5 | Asset Feedback Due | Design Production |  | Creative
Draft Sephora Catalog & PDP Copy Due | 5 | DTC & Amazon Final Assets Due | Design Production |  | Marketing
Final DTC PDP Copy & Reviews Due | 3 | Draft Sephora Catalog & PDP Copy Due | Design Production |  | Marketing
Social Campaign | date range that needs to be manually added once social plan is finalized & asset request form is final | Finalize Asset Requests | Design Production |  | Social
Launch Event | date that needs to be manually added when finalized based on launch event planning (outside of GTM) | Set Up Event Planning Meeting (if appl.) | Design Production |  | Marketing
OOH Campaign | date that needs to be manually added when finalized based on OOH planning (outside of GTM) | Set Up OOH Planning (if appl.) | Design Production |  | Marketing